**DELIVERABLE AND MILESTONE TABLE**

**Activities on Nutrition, Maternal and Child Health**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **MILESTONES** | **DELIVERABLES** | **FREQUENCY** |
|  | 1. Current Operational Manuals and policies to reflect operational changes based on recommendations from pre-award assessment. 2. Recruit technical staff 3. Nutrition Officer 4. Project Officer 5. Project Coordinator 6. Development of an initial Workplan covering activities over the period of this award | 1. Updated operational manual signed by the Board. 2. Employment Contract letters, Acceptance letter, CV. 3. Workplan containing activities, expected outputs, outcomes, and timelines | Once |
|  | Establish an office accommodation at the district level | Rent Agreement |
|  | Initial Community Entry | Report on Community Entry, including communities and dates of engagement, persons engaged and outcome of engagement |
|  | Engage community leaders and sub-districts to select 3 Community Health Volunteers (CHV) per community | List of Community Health Volunteers selected in each community | Annual |
|  | Mobilize pregnant women in the community and sensitize them on pregnancy schools and support Midwives and Community Health Nurses to establish pregnancy schools in their selected communities or by cluster of communities. | List of pregnant women registered per pregnancy school per community. |
|  | Community durbars held (1 in each community) to outdoor trained CHVs and their scope of work.  Registration and collection of basic information data of all children under 5 years, pregnant women and other women in reproductive age (15 – 49 years) and aged | Summary report on community durbars indicating the number of participants per community disaggregated by gender, age, and pictures.  Details of number of children and pregnant women and other WRA, aged registered by community and district |
|  | Support the conduct of community-based growth promotion sessions and home visits by CHNs/CHOs and CHVs  Provide technical support to communities on ASBC-led CHAPs implementation  Support midwives and CHNs to facilitate community pregnancy schools | Summarized monthly sessions, including number of home visits conducted, and pictures  Summary of Updates on CHAPs implementation  Summarized pregnancy school sessions, including number of women who participated per trimester | Monthly |
|  | Support midwives to hold Graduation ceremonies for pregnancy school participants who deliver at health facilities | Highlights from graduation ceremony with number of graduands, pictures | Quarterly |
|  | Carry out community engagements on child protection issues using UNICEF child protection toolkits.  Carry out community engagements to create demand for Family Planning, MCH and nutrition services in 10 Communities.  Identify and engage male and male groups on their role in improving the nutrition and health of CU5 and WRA | Reports on community engagements, Attendance, and Pictures  Educational materials developed and used, Pictures and Attendance  Summary report of number of persons per engagement session and issues identified, discussed and solutions proposed. | Bi-annually |